## Sheet1
Project Information
Project name: |  | Line and Sign detection |  |  | RISK MATRIX
Project Start date: |  | 2020-10-27
Estimated completion date: |  | 2021-02-11
Project Status: |  | On Track
Risk Number | Risk Description | Impact of Risk | Probality of Occurrence | Impact Score | Mitigation Strategy | Domain
R1 | Failure of Camera | Can lead to accidents due to non-capture of signs and line. | 0.2 | 3 | Switch to manual mode. | Hardware
R2 | Rainy or snowy conditions while driving | Can be fatal to the system due to water intrusion. Also lines cannot be detected by them system. | 0.8 | 3 | The system must be in a waterproof box. Do no use to it to drive in rainy and swony conditions. | Hardware
R3 | Overheating of the system processor | Can potentially damage the processor in the system. | 0.9 | 1 | Proper heat dissipation methods such as heat sink shall be installed to minimaized the hating effect. | Hardware
R4 | Inaccurate detection of lane line | Can lead the car to go off the road. | 0.3 | 3 | Autonomous driving should be done only when there is adequate lighting is available. | Software
R5 | Inaccurate detection of traffic lights and road signs. | Can lead to accidents. | 0.4 | 3 | By training the software to detect the signals with over 60% accuracy | Software
R6 | Processor failure | Can lead to the crash of the system. | 0.15 | 3 | Regular inspections are needed. | Hardware.
R7 | Entire Software failure | Can lead to the crash of the whole system. | 0.25 | 3 | Regular inspections and periodic updates are needed. Testing of the software according to the test strategies. | Software.
1 - LOW
2 - MEDIUM
3 - HIGH